## March progress update
Progress update on SIS
Information sorted by Cllr (column A)
As at 31st March
* denotes activity that will result in an output being sent by Project Manager to County Councillor
Current Member | HSPR | Scheme Name/ Proposal | Location | District | Ward | Project Manager | Portfolio (budget coding) | Current Budget (from Monitoring) | Current Estimated Cost (000) | Programmed Construction Start Date (from Monitoring) | Latest Comments to Members | Feasibility Commissioned | Feasibility Completed * | Design Commissioned | Outline Design | Consultation plan issued * | Detailed Design | Issue of Task Order * | Construction Mobilisation | Construction
Cllr Best, Mike | TI004379 | Market Street, Crewkerne traffic management | Crewkerne | South Somerset | Crewkerne | Martyn Evans 01823 359534 |  |  | TBC |  | Agreement has been reached with BT/Openreach in relation to their cover. Proposed construction start date of 04/04/2022 | [8 empty] | Apr 22
Cllr Best, Mike | TI004359 | Maiden Beech Crossroads junction improvements | Maiden Beach Crossroads |  | Crewkerne | Martyn Evans 01823 359534 |  |  | TBC |  | Design options being considered.Topo survey results have been revieved and a speed review proposal has been shared with TM and they have given approval. Some veg clearance for this scheme has been added to a bigger package of works. New designer appointed. | N/A | N/A |  |  | TBC |  | May/ Jun 22
Cllr Bloomfield, Neil | TI004372 | Highway/Ash speed reduction and pedestrian safety improvements | Highway/Ash |  | Ash | Martyn Evans 01823 359534 |  |  | TBC |  | Speed survey complete. Ped survey reviewed.Meeting to discuss options sheduled for 31st March. | N/A | N/A
Cllr Bown, Ann | TI004310 | Kendale Road and junction of Chilton Street, Bridgwater traffic calming | Kendale Road | Sedgemoor | Bridgwater West | Stuart Fountain 01823 358025 |  |  | 40 |  | Substantially complete, minor lining outstanding. RSA 3 to be commisioned
Cllr Broom, Amanda | TI004316 | Glynswood, Chard pedestrian crossing improvements | Glynswood, Chard | South Somerset | Chard North | Stuart Fountain 01823 358025 |  |  | 40 |  | Task Order issued 03/09/21 Work substantially completed 18/03 Wigwags outstanding | [8 empty] | Jan 22
Cllr Broom, Amanda | TI004330 | Furnham Road, Chard pedestrian crossing improvements | Furnham Road, Chard |  | Chard Town | Stuart Fountain 01823 358025 |  |  | TBC |  | Scheme sunstanitally complete 18th February.
Cllr Chilcott, Mandy | TI004339 | Townsend Road pedestrian crossing improvements | Minehead |  | Minehead | Andy Nellist 01823 357341 |  |  | TBC |  | Construction substantially complete (minor road marking outstanding due to parked vehicles).
Cllr Dance, Adam | TI004341 | Merriott pedestrian improvements | Merriott |  | Merriott | Stuart Fountain 01823 358025 |  |  | TBC |  | Construction started 28th March. | [8 empty] | Mar 22
Cllr Davies, Hugh/ Cllr Lawrence, Christine, Cllr Rigby, Mike | TI004390 | A358 Williton to Crosskeys RAB |  |  |  | Richard Mills |  |  |  |  | New road safety commission. Data review being undertaken and outline design commencing
Cllr Filmer Bob | TI004340 | A38/Biddisham Lane junction safety improvements (VAS) | A38 |  | Biddisham | Andy Nellist 01823 357341 |  |  | TBC | Q3 20/21 | Highway boundary disputed by adjacent landowner, being investigated by SCC Legal team to confirm position prior to agreement with landowner. | N/A | N/A | [6 empty] | TBC
Cllr Groskop, Anna | TI004264 | Wincanton Town Centre 20mph | Wincanton Town Centre | South Somerset | Wincanton & Bruton | Stuart Fountain 01823 358025 | WSP | 0 | 35 |  | On hold - discussion to be had regarding now 'unlocking' Contact made with development Liasing team to confirm if scheme can comence |  |  |  |  | TBC
Cllr Hall, David | TI004384 | Kings Drive, Bridgwater improved crossing facilities | Kings Drive, Bridgwater | Sedgemoor | Bridgwater East and Bawdrip | Richard Mills |  |  | TBC |  | Complexities of scheme have been re-discussed with design team. Requirement for land to deliver improvement remains | N/A | N/A
Cllr Hall, David / Cllr Huxtable, David | TI004375 | A39 Silverfish to Pipers Inn road safety | A39 Silverfish to Pipers | Sedgemoor | Bridgwater East and Bawdrip / King Alfred | Andy Nellist 01823 357341 | #N/A |  | 60 |  | Task Order issued. Queries responded to. Mobilising for construction. | N/A | N/A | [6 empty] | TBC
Cllr Hall, David/ Cllr Loveridge, Dave |  | Bristol Road Corridor IMP - Dunball to Express park Corridor 1 - Element 2 | Bridgwater | Sedgemoor | Various | Richard Mills |  |  |  |  | Toucan and associated works substantially complete. Toucan to be commissioned. Phase 2 design amendemnts being made | [8 empty] | Jan 22
Cllr Hall, David/ Cllr Loveridge, Dave | MN004167.3 | Bristol Road Corridor IMP - Express Park To Town Centre (West Quay) Via River Parrett - Corridor 1 - Element 3 - No.3 | Bridgwater | Sedgemoor | Various | Richard Mills | 0 |  |  |  | Task order issued. Works programmed start to be agreed | [8 empty] | May 22
Cllr Ham, Phillip | TI004369 | Coleford traffic management | Coleford |  | Coleford | Andy Nellist 01823 357341 |  |  | TBC |  | Construction of 'Interim' scheme 28/3/2022 to 30/3/2022.
Cllr Hewit-Cooper, Nigel | TI004313 | B3136 Lamberts Hill Shepton Mallet road safety | Shepton Mallet | Mendip | Mendip South | Martyn Evans 01823 359534 |  |  | TBC |  | Last phase will involve junction reshaping with the newly aquired land and as a result of having to apply for hedge removal notice this phase will likley start after bird nesting is finished in Sept 2022. Plans ongoing to relocate BT pole in the interim. | N/A | N/A | [6 empty] | Sep 22
Cllr Hewitt-Cooper, Nigel | TI004347 | A37 (north of junction with B3153) pedestrian safety | Lydford |  | Lydford | Andy Nellist 01823 357341 |  |  | TBC |  | Construction completed. RSA3 completed and minor remedial work identified. | N/A | N/A
Cllr Hewitt-Cooper, Nigel | TI004358 | A361 Pilton pedestrian crossing improvements (near bus stop) | Pilton |  | Croscombe & Pilton | Andy Nellist 01823 357341 |  |  | TBC |  | Advanced vegetation undertaken. Further works to be programmed to fit network availability. | [8 empty] | Apr 22
Cllr Hunt, James | TI004389 | A38 Perry Elm RAB to Devon CB |  |  |  | Martyn Evans 01823 359534 |  |  |  |  | New road safety commission. Advance work on police camera platforms instructed to Milestone ( phase 1) Task order has been issued .The veg cut back for this scheme will be added to a bigger package of works. Brief for main scheme speed review issued to WSP ( phase 2). Veg clearance for Phase 2 has also been added to a bigger package of works. |  |  |  |  | Feb 22 Phase 1 |  | Feb 22 Phase 1 |  | Apr 22
Cllr Keating, Mark | TI004315 | Halves Lane, East Coker pedestrian safety improvements | East Coker | South Somerset | Coker | Martyn Evans 01823 359534 |  |  | TBC |  | RSA1 received back for comment. Still awaiting ecology approval regarding trees. | N/A | N/A |  |  |  | Apr 22 | May 22
Cllr Keating, Mark | TI004346 | Newton Road, Stoford pedestrian safety | Newton Road, Stoford |  | Barwick & Stoford | Stuart Fountain 01823 358025 |  |  | TBC |  | Detailed designof hybrid scheme progressing. Some advance vegetation cutting has been undertaken | [6 empty] | May 22
Cllr Kendall Andy | TI004349 | Reckleford, Yeovil bus stop improvements | Reckleford, Yeovil |  | Yeovil Central | Martyn Evans 01823 359534 |  |  | TBC |  | First trial holes completed. Results show that no issue with gas main found but some BT services will need a C4 survey to be carried out to allow the scheme to move forward. One further cover to be lifted with road closure arranged.A date is still to be confimed | N/A | N/A |  |  |  |  | May 22
Cllr Kendall, Andy / Cllr Purbrick, Faye | TI004385 | Reckleford, Yeovil road safety improvements | Reckleford, Yeovil | South Somerset |  | Martyn Evans 01823 359534 |  |  | TBC |  | Design to progress in 2 phases whilst the cattle market development remains pending. Instruction for phase 1 sent to designers to progress. Ped survey complete. Designer has confirmed results.Scheme now ready for consultation stage. | N/A | N/A |  |  | 2022-04-01 |  | May 22
Cllr Lawrence, Christine / Cllr Chilcott, Mandy | TI004267 | West Somerset Community College, Minehead, pedestrian crossing improvements | West Somerset College, A39 Minehead | West Somerset | Minehead / Dunster | Andy Nellist 01823 357341 | In House | 0 | 100 |  | Crossing commissioned. Minor remedial works identified. RSA3 ro be requested.
Cllr Lawrence, Christine / Cllr Chilcott, Mandy | MN004258 | Minehead to Carhampton footway/ cycleway improvements | Minehead/ Dunster/ Carhampton |  |  | Richard Mills |  |  |  |  | Task order for phase 1 issued. Traffic Management restriction will influence programme. Meeting arranged to disucss and agree. Phase 2/3 design progressing | [8 empty] | May 22
Cllr Lock, Tony | MN004252 | Lyde Road, Yeovil cycle route | Lyde Road, Yeovil | South Somerset | Yeovil East | Martyn Evans 01823 359534 | WSP |  | TBC |  | Ecology survey has been completed.Change to unsegregated use to satisfy LTN/120 assesment. RSA2 has been received from audit and awaiting designer review beofre task order can be issued. | [6 empty] | Apr 22
Cllr Loveridge, Dave | TI004354 | Parkway / Fairfax Street, Bridgwater cycle safety | Bridgwater | Sedgemoor | Bridgwater North and Central | Stuart Fountain 01823 358025 |  |  |  |  | Scheme complete 25th Feb, few remedials to be agreed and carried out.
Cllr Nicholson, Frances | TI004277 | Simonsbath Traffic Management | B3223 Simonsbath | West Somerset | Dulverton and Exmoor | Stuart Fountain 01823 358025 | In House | 0 | 25 |  | At outline design. Meeting held with County Councilor and environmental groups. Additional topo carried out added agreed additional work to be carried out to install anti parking measures - order for interim bollards issued. |  |  |  |  | TBC |  | Jul 22
Cllr Noel, Graham | TI004360 | Coxley pedestrian crossing improvements | Coxley |  | St Cuthbery Out | Stuart Fountain 01823 358025 |  |  | TBC |  | Substantially complete. (Minor outstanding stud work to be completed with developer resurfacing) | N/A | N/A
Cllr Oliver, Linda | TI004348 | B3090 Oldford Hill junction with Cuckoo Ln and Gypsy Lane, Frome junction improvements | Frome |  | Frome | Andy Nellist 01823 357341 |  |  | TBC |  | Task Order issued. TRO consultation underway. 20WLS now to be delivered separately. Mendip District Council requiring lease agreement for speed enforcement hardstanding. | N/A | N/A | [6 empty] | TBC
Cllr Paul, Clare | TI004365 | B3153 Pitney (Langport to Somerton) speed review | B3153 Langport to Somerton |  | High Ham, Pitney, Somerton | Martyn Evans 01823 359534 |  |  | TBC |  | Traffic Management Team support to progress scheme discussed. Scheme extents have been confirmed. Designer to visit site. | N/A | N/A
Cllr Pullin, Mike | TI004234 | Old Down to Chilcompton - speed review & improved pedestrian facilities | B3139 between Old Down and Chilcompton | Mendip | Mendip Hills | Andy Nellist 01823 357341 | In House | 41791 | 250 | 0 | Task Order issued for Phase 1 (TM scheme), RSA completed and TRO requested. Draft design for Phase 2 (footway) being consulted on and preparing for RSA. | [8 empty] | May/ Jun 22
Cllr Pullin, Mike | TI004278 | B3139 , (B3135 Burnt Wood Crossroads to A37 Old Down Crossroads) Whitnall Corner Road Safety Improvements | B3139 , (B3135 Burnt Wood Crossroads to A37 Old Down Crossroads) | Mendip | Mendip Hills | Andy Nellist 01823 357341 | In House | 0 | 400 |  | Design package being finalised for construction issue. Further Ecological study work underway. Land negotiations continue. Budget issues to be addressed. | [6 empty] | TBC
Cllr Pullin, Mike | TI004305 | B3135 Bath Road to Old Down | B3135 Bath Road | Mendip | Mendip Hills | Andy Nellist 01823 357341 | In House | 30 | 30 |  | Site review completed and outstanding/ remedial works identified to contractor. RSA3 underway.
Cllr Pullin, Mike | TI004332 | Beacon Hill Crossroads road safety | Beacon Hill Crossroads (south of Oakhill) | Mendip | Mendip Hills | Andy Nellist 01823 357341 | #N/A |  | 40 |  | Construction complete. RSA3 required. Damaged/ missing give way sign to be replaced.
Cllr Pullin, Mike | TI004387 | Roemeade junction with A37 road safety |  |  | Ashwick | Richard Mills |  |  |  |  | Detailed design progressing | [6 empty] | Jul 22
Cllr Pullin, Mike | TI004388 | Roemeade/ B3135 road safety |  |  | St Cuthbert Out | Richard Mills |  |  |  |  | Detailed design progressing | [6 empty] | Jul 22
Cllr Revans, Bill | TI004318 | North st / High st / Dancing Hill, North Petherton junction improvements | North Petherton | Sedgemoor | North Petherton | Stuart Fountain 01823 358025 |  |  | TBC |  | Site Visit completed with Land Owner and Farm owner, both on board with the scheme Retaining wall within hedge to be moved discovered will need further topo. Due to many factors redesign to be looked into to get the most out of the scheme. |  |  |  |  | TBC
Cllr Revans, Bill | TI004329 | East of North Petherton to North Newton traffic management (when lights show) | North Petherton |  | North Petherton | Stuart Fountain 01823 358025 |  |  | TBC |  | Task order issued 25/11 TRO's advertised, and sealed. Construction to start 25/04 | [8 empty] | Apr 22
Cllr Ruddle, Dean | TI004274 | West Street, Somerton pedestrian improvements (one way) | West Street, Somerton | South Somerset | Somerton | Martyn Evans 01823 359534 | In House | 0 | 50 |  | Experimental One way system in operation. Design progressing on permanent solution
Cllr Ruddle, Dean | TI004344 | Kingweston Road and Ilchester Road, Charlton Mackrell speed reduction | Charlton Mackrell |  | The Charltons | Andy Nellist 01823 357341 |  |  | TBC |  | TRO consultation successfully concluded and order to be sealed. Construction start programmed for 4 April 2022. | N/A | N/A | [6 empty] | Apr 22
Cllr Ruddle, Dean | TI004366 | High Street, Castle Street and Queen Street, Keinton Mandeville traffic management | Keinton Mandeville |  | Keinton Mandeville | Andy Nellist 01823 357341 |  |  | TBC |  | Task Order issued. Mobilising for construction. | [8 empty] | May 22
Cllr Ruddle, Dean | TI004382 | Behind Berry traffic management | Somerton | South Somerset | Somerton | Stuart Fountain 01823 358025 |  |  | TBC |  | Further options received to include one way through problematic junction. New options currently under consultation with town council. | [6 empty] | TBC
Cllr Ruddle, Dean | TI004391 | Langport Road, Somerton | Somerton | Som | Somerton | Martyn Evans 01823 359534 |  |  |  |  | Consultation package approved by County Cllr.Next stage to consult with wider community and statutory consultees | [5 empty] | Apr 22
Cllr Taylor, Nigel | TI004353 | Shipham speed reduction and traffic management | Shipham |  | Cheddar | Stuart Fountain 01823 358025 |  |  | TBC |  | Construction complete. Minor remedials to be undertaken | N/A | N/A
Cllr Thorne, John | TI004362 | Ruishton lane, Ruishton pedestrian safety improvements | Ruishton |  | Ruishton | Andy Nellist 01823 357341 |  |  | TBC |  | Parish council support confirmed following public consultation. Detailed design underway. | [6 empty] | May 22
Cllr Thorne, John | TI004386 | Chillander Cross (Corfe Hill) road safety |  |  | Otterford | Richard Mills |  |  |  |  | Detailed design progressing | [6 empty] | Jul 22
Cllr Vijeh, Linda | TI004342 | Winsham pedestrian safty improvements (including possible 20 WLS or limit) | Winsham |  | Winsham | Andy Nellist 01823 357341 |  |  | TBC |  | Task Order Issued, but mobilisation pending determination of TRO following objection received. | N/A | N/A | [6 empty] | 2022-05-01
Cllr Wallace, William | TI004361 | A30 Milborne Port, Pedestrian Crossing and Traffic Calming | A30 Crackmore |  | Milborne Port | Martyn Evans 01823 359534 |  |  | TBC |  | Position of some utilities have been confirmed. Task Order issued for further investigation of BT and Gas infrastructure. Start onsite for further trial holes 11th April. RSA2 received from audit and being reviewed by designer. | [6 empty] | Apr 22
Cllr Wallace, William | TI004370 | Templecombe review of exiting traffic calming build out | High street, Templecombe |  | Abbas and Templecombe | Martyn Evans 01823 359534 |  |  | TBC |  | Site meeting has taken place with Parish Council and Cllr. Way forward agreed. Plan being drafted for presenting at May PC meeting | N/A | N/A |  |  | Apr 22
Formulas:
Q3 20/21 = VLOOKUP([HSPR],[1]Monitoring!$E4:BS257,64,FALSE)