Information

for Somerset Waste Board and Partner Authority Members

| From: | David Oaten, Contracts Manager – Treatment & Infrastructure, Somerset Waste Partnership |
| --- | --- |

| Date: | 8th November 2017 |
| --- | --- |

| To: | All Members of the Somerset Waste Board All Members of Somerset County Council Members of Partner District Authorities via the Senior Management Group Representatives |
| --- | --- |

# New Waste Treatment Facility Update: moving away from landfill

Summary

In line with the Somerset Waste Board’s longstanding commitment to reduce the overall environmental impact of our residual waste, through moving away from highly taxed landfill, we are progressing well with this project. The overall contract and build schedule for the New Waste Treatment Facility and Waste Transfer Stations continues to remain on track, with plant commissioning tests expected to commence toward the mid to end of 2019 in preparation for the April 2020 start date. In addition to the environmental benefits, this will deliver £1.3m annual MTFP savings from now until March 2020 to the disposal authority (Somerset County Council). Further updates will be provided at key milestones in the project.

Background

Since 2014 the Somerset Waste Board’s Business Plan has included a target to seek long term affordable and sustainable alternatives to landfill for material that cannot be avoided or recovered.  This aimed to reduce the overall environmental impact of residual waste, to introduce compliant, competitive and affordable arrangements for the transfer, haulage and treatment of residual waste and to meet Somerset County Council’s MTFP savings target from 2016/17 onwards.

Following protracted negotiations with the incumbent residual waste service provider (Viridor Ltd), a new waste treatment facility contract was approved by the Somerset Waste Board at its meeting in February 2017.  Moving away from landfill will be enabled by Viridor constructing an Energy from Waste plant at Avonmouth, serviced by two Waste Transfer Stations at Dimmer (Castle Cary) & Walpole (Pawlett). The new service is scheduled to commence in April 2020.

Update on Progress

Since signing the New Waste Treatment Facility 2 Contract with Viridor Ltd on the 29th of March 2017 (Agreement Date), the 3 contractual conditions have now been achieved;

- Viridor was granted Planning Permission in respect of the construction of the Walpole Transfer Station on 13th March 2017

- No Procurement Challenges were received within six months of the agreement date (i.e. by 30th September 2017); and

- Viridor appointed construction contractors for the Avonmouth plant (CNIM S.A. and Clugston Construction Ltd)  on 30th March 2017

As a result of satisfying these contract conditions and formally exchanging notices with Viridor, the ‘Trigger Date’ in the contract has been achieved. This means that £1.3m annual MTFP savings to March 2020 are secured, starting in the current financial year.  Savings of £650k having been achieved in 2016/17.

Good progress has been made with the construction of the Avonmouth Energy from Waste plant with;

- The secant piling having been completed and  the excavation of the waste bunker having commenced

- Piling has now commenced on the other areas of the site, e.g. the boiler hall

- An order has been placed for the boiler

- Temporary offices are on site and now in occupation

The next steps through this Winter and early Spring 2018 are;

- Works continue at Avonmouth, with a possible SWB Member visit to be arranged for Spring 2018 – once works commence above ground level

- Viridor plan to start building the Dimmer Waste Transfer Station in February 2018, with a scheduled completion and operationally ready date of February 2019

- Viridor plan to start building the Walpole Waste Transfer Station in March 2018, with a scheduled completion and operationally ready date of May 2019

- The minor changes necessary to Somerset’s Recycling Centre network (for example to signage and bin configuration) are being assessed. This will not reduce the range of materials accepted at Recycling Centres.

- The interdependencies with how we collect waste are being reflected in our future plans for collection services – for example different types of refuse vehicles may be required as they will no longer need to be able to cope with driving over a landfill site.

| For more information please contact: | Name: David Oaten Email: david.oaten@somersetwaste.gov.uk Tel No: 01823 625721 |
| --- | --- |

# Text boxes

Sheet Number:

2017-21/31